28-Day Development

Schedule

AI-Powered Applicant Tracking System

Team: 5 Developers | Duration: 4 Weeks | Sprints: 4

Methodology: Agile Scrum with Daily Standups

Date: June 2026

# Team Overview

| Developer | Domain | Key Deliverables |
| --- | --- | --- |
| Dev 1: Auth & Security | Authentication, RBAC, Security | JWT auth, password hashing, Helmet, rate limiting, input validation |
| Dev 2: Job Management | Jobs, Applications, Search | Job CRUD, application system, search/filter, dashboard APIs |
| Dev 3: Resume & AWS | File Upload, S3, Resumes | Multer integration, S3 storage, resume management, file security |
| Dev 4: AI Integration | Gemini API, Scoring, Ranking | AI analysis engine, scoring algorithm, candidate ranking, summaries |
| Dev 5: Frontend & Deploy | React UI, Vercel, Testing | Complete responsive UI, Material Design, deployment, E2E tests |

# Week 1: Project Setup & Foundation (Days 1-7)

## Day 1 (Monday)

| Dev 1 | Auth/Security | Setup: Initialize GitHub repo, branching strategy, CI/CD pipeline scaffold |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Design Job collection schema, create Mongoose model with validation |
| Dev 3 | Resume/AWS | AWS: Create S3 bucket, configure IAM roles, setup CORS policies |
| Dev 4 | AI/Ranking | AI: Research Gemini API docs, create API key, test basic prompts |
| Dev 5 | Frontend | Frontend: Initialize React project with Vite, install Material UI, setup folder structure |

## Day 2 (Tuesday)

| Dev 1 | Auth/Security | Setup: Configure ESLint, Prettier, Husky pre-commit hooks |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Implement Job CRUD controller and service layer |
| Dev 3 | Resume/AWS | AWS: Implement S3 upload service with Multer integration |
| Dev 4 | AI/Ranking | AI: Design scoring algorithm, create prompt templates |
| Dev 5 | Frontend | Frontend: Create routing structure, layout components, navigation shell |

## Day 3 (Wednesday)

| Dev 1 | Auth/Security | Setup: Setup MongoDB Atlas cluster, configure connection strings |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Implement job search, filtering, pagination APIs |
| Dev 3 | Resume/AWS | AWS: Implement file validation (type, size), filename sanitization |
| Dev 4 | AI/Ranking | AI: Implement resume text extraction using pdf-parse |
| Dev 5 | Frontend | Frontend: Create login/register pages, form validation with React Hook Form |

## Day 4 (Thursday)

| Dev 1 | Auth/Security | Auth: Implement User schema with bcrypt password hashing |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Add job status management (draft, publish, close, archive) |
| Dev 3 | Resume/AWS | AWS: Generate presigned URLs for secure resume download |
| Dev 4 | AI/Ranking | AI: Implement skill extraction prompt, parse structured output |
| Dev 5 | Frontend | Frontend: Integrate Axios with JWT interceptor, create auth context |

## Day 5 (Friday)

| Dev 1 | Auth/Security | Auth: Implement JWT token generation (access + refresh) |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Create recruiter job dashboard API endpoint |
| Dev 3 | Resume/AWS | AWS: Integrate S3 upload into resume service, error handling |
| Dev 4 | AI/Ranking | AI: Build semantic matching between skills and job requirements |
| Dev 5 | Frontend | Frontend: Create protected route components, role-based access guards |

## Day 6 (Saturday)

| Dev 1 | Auth/Security | Auth: Implement token refresh endpoint, httpOnly cookie setup |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Write unit tests for Job service and controller |
| Dev 3 | Resume/AWS | AWS: Write tests for S3 upload/download, validation edge cases |
| Dev 4 | AI/Ranking | AI: Implement weighted scoring algorithm (40/30/15/15) |
| Dev 5 | Frontend | Frontend: Create Admin dashboard page, stats cards component |

## Day 7 (Sunday)

| Dev 1 | Auth/Security | Auth: Implement logout with token invalidation |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Add job expiration logic, scheduled cleanup task |
| Dev 3 | Resume/AWS | AWS: Implement resume deletion, S3 lifecycle policies |
| Dev 4 | AI/Ranking | AI: Build AI summary generation, skill gap analysis |
| Dev 5 | Frontend | Frontend: Create User Management page with data table |

# Week 2: Core Features (Days 8-14)

## Day 8 (Monday)

| Dev 1 | Auth/Security | Auth: Add RBAC middleware, role verification on protected routes |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Implement public job listing API (unauthenticated access) |
| Dev 3 | Resume/AWS | Resume: Create Resume collection schema, link to User model |
| Dev 4 | AI/Ranking | AI: Integrate Gemini API client with retry logic, error handling |
| Dev 5 | Frontend | Frontend: Build Job Board page with search and filter components |

## Day 9 (Tuesday)

| Dev 1 | Auth/Security | Auth: Add password reset flow with email token |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Create job application endpoint (Application collection) |
| Dev 3 | Resume/AWS | Resume: Build resume upload API endpoint with Multer + S3 |
| Dev 4 | AI/Ranking | AI: Implement full analysis pipeline: parse → extract → match → score |
| Dev 5 | Frontend | Frontend: Create Job Details page, Apply button with resume upload |

## Day 10 (Wednesday)

| Dev 1 | Auth/Security | Auth: Implement input validation with Joi schemas |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Add duplicate application prevention (compound index) |
| Dev 3 | Resume/AWS | Resume: Build resume download endpoint (presigned URL) |
| Dev 4 | AI/Ranking | AI: Create candidate ranking API (sort by overallScore descending) |
| Dev 5 | Frontend | Frontend: Build Applicant Dashboard, application history timeline |

## Day 11 (Thursday)

| Dev 1 | Auth/Security | Security: Add Helmet.js, configure security headers |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Implement job analytics (views, application counts) |
| Dev 3 | Resume/AWS | Resume: Add resume versioning support in S3 |
| Dev 4 | AI/Ranking | AI: Build AI analysis caching to reduce API costs |
| Dev 5 | Frontend | Frontend: Create Recruiter Dashboard with pipeline overview |

## Day 12 (Friday)

| Dev 1 | Auth/Security | Security: Implement rate limiting (login, API endpoints) |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Add job templates for quick posting |
| Dev 3 | Resume/AWS | Resume: Implement resume deletion and cleanup |
| Dev 4 | AI/Ranking | AI: Add AI explanation feature (why candidate scored X) |
| Dev 5 | Frontend | Frontend: Build Candidate Ranking page with sortable table |

## Day 13 (Saturday)

| Dev 1 | Auth/Security | Security: Add CORS configuration, XSS protection |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Write integration tests for job APIs |
| Dev 3 | Resume/AWS | Resume: Write tests for upload/download flow |
| Dev 4 | AI/Ranking | AI: Write tests for scoring algorithm accuracy |
| Dev 5 | Frontend | Frontend: Build Application Pipeline Kanban board |

## Day 14 (Sunday)

| Dev 1 | Auth/Security | Security: Implement MongoDB sanitization (NoSQL injection prevention) |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Jobs: Add job categories, tags, advanced filters |
| Dev 3 | Resume/AWS | Resume: Add bulk operations for resume management |
| Dev 4 | AI/Ranking | AI: Implement batch processing for multiple candidates |
| Dev 5 | Frontend | Frontend: Create Analytics page with charts and date filters |

# Week 3: Integration & Polish (Days 15-21)

## Day 15 (Monday)

| Dev 1 | Auth/Security | Auth: Add social login preparation (Google OAuth scaffold) |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Notification: Design Notification collection schema |
| Dev 3 | Resume/AWS | Email: Setup Nodemailer with SMTP transport |
| Dev 4 | AI/Ranking | AI: Implement AI interview question generator |
| Dev 5 | Frontend | Frontend: Create notification bell component, toast system |

## Day 16 (Tuesday)

| Dev 1 | Auth/Security | Auth: Implement account lockout after failed attempts |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Notification: Build notification service (create, mark read, list) |
| Dev 3 | Resume/AWS | Email: Create Handlebars email templates (application received) |
| Dev 4 | AI/Ranking | AI: Build resume improvement suggestions feature |
| Dev 5 | Frontend | Frontend: Integrate notifications into layout, real-time badge |

## Day 17 (Wednesday)

| Dev 1 | Auth/Security | Auth: Add audit logging for auth events |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Notification: Implement notification preferences per user |
| Dev 3 | Resume/AWS | Email: Create interview invitation email template |
| Dev 4 | AI/Ranking | AI: Implement skill gap analysis dashboard data |
| Dev 5 | Frontend | Frontend: Create Settings page, notification preferences |

## Day 18 (Thursday)

| Dev 1 | Auth/Security | API: Add global error handling middleware |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Notification: Trigger notifications on status changes |
| Dev 3 | Resume/AWS | Email: Create status update and rejection email templates |
| Dev 4 | AI/Ranking | AI: Build candidate recommendation engine (similar jobs) |
| Dev 5 | Frontend | Frontend: Polish UI, add loading states, error boundaries |

## Day 19 (Friday)

| Dev 1 | Auth/Security | API: Implement request logging with Morgan |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Notification: Add push notification preparation (service worker) |
| Dev 3 | Resume/AWS | Email: Integrate email sending into application lifecycle |
| Dev 4 | AI/Ranking | AI: Add confidence scores to AI predictions |
| Dev 5 | Frontend | Frontend: Implement responsive design, mobile optimization |

## Day 20 (Saturday)

| Dev 1 | Auth/Security | Testing: Write end-to-end auth flow tests |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Notification: Write unit tests for notification service |
| Dev 3 | Resume/AWS | Email: Test all email templates with real SMTP |
| Dev 4 | AI/Ranking | AI: Calibrate scoring weights based on test data |
| Dev 5 | Frontend | Frontend: Write component tests with React Testing Library |

## Day 21 (Sunday)

| Dev 1 | Auth/Security | Testing: Run security scan with OWASP ZAP |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Integration: Full feature integration testing |
| Dev 3 | Resume/AWS | Integration: Email delivery verification |
| Dev 4 | AI/Ranking | AI: Performance optimization, caching strategy |
| Dev 5 | Frontend | Frontend: Cross-browser testing, accessibility audit |

# Week 4: Testing & Deployment (Days 22-28)

## Day 22 (Monday)

| Dev 1 | Auth/Security | DevOps: Setup Render.com backend deployment |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | DevOps: Setup Vercel frontend deployment |
| Dev 3 | Resume/AWS | DevOps: Configure environment variables for production |
| Dev 4 | AI/Ranking | AI: Final AI prompt tuning based on recruiter feedback |
| Dev 5 | Frontend | Frontend: Performance optimization, lazy loading, code splitting |

## Day 23 (Tuesday)

| Dev 1 | Auth/Security | DevOps: Configure MongoDB Atlas production cluster |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | DevOps: Setup CI/CD GitHub Actions workflow |
| Dev 3 | Resume/AWS | DevOps: Configure AWS S3 CORS for production domain |
| Dev 4 | AI/Ranking | AI: Add fallback scoring when AI API is unavailable |
| Dev 5 | Frontend | Frontend: Build production bundle, optimize assets |

## Day 24 (Wednesday)

| Dev 1 | Auth/Security | Testing: Full API integration test suite |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Testing: Frontend E2E tests with Cypress |
| Dev 3 | Resume/AWS | Testing: Load testing with k6 (100 concurrent users) |
| Dev 4 | AI/Ranking | Integration: End-to-end AI analysis verification |
| Dev 5 | Frontend | Frontend: Final UI polish, animations, transitions |

## Day 25 (Thursday)

| Dev 1 | Auth/Security | Testing: Security penetration testing |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Bug Fix: Address integration test failures |
| Dev 3 | Resume/AWS | Bug Fix: Fix S3 upload issues in production |
| Dev 4 | AI/Ranking | Integration: Verify AI scoring accuracy with real resumes |
| Dev 5 | Frontend | Frontend: Fix responsive layout issues |

## Day 26 (Friday)

| Dev 1 | Auth/Security | Testing: Final regression test suite |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Bug Fix: Performance optimization |
| Dev 3 | Resume/AWS | Bug Fix: Email delivery troubleshooting |
| Dev 4 | AI/Ranking | Integration: Final AI pipeline verification |
| Dev 5 | Frontend | Frontend: Final bug fixes, error handling improvements |

## Day 27 (Saturday)

| Dev 1 | Auth/Security | Deploy: Deploy backend to Render production |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Deploy: Deploy frontend to Vercel production |
| Dev 3 | Resume/AWS | Deploy: Configure production monitoring (LogRocket/Sentry) |
| Dev 4 | AI/Ranking | Docs: Write API documentation (Swagger/OpenAPI) |
| Dev 5 | Frontend | Docs: Create user guide for admin/recruiter/applicant |

## Day 28 (Sunday)

| Dev 1 | Auth/Security | Final: Production smoke tests |
| --- | --- | --- |
| Dev 2 | Jobs/Apps | Final: Team demo preparation |
| Dev 3 | Resume/AWS | Final: Backup and disaster recovery verification |
| Dev 4 | AI/Ranking | Final: Performance benchmark documentation |
| Dev 5 | Frontend | Final: Project handoff, README completion |